7

Working with a Logic Model

We’ve defined the key terms that we will need to use with our Logic Model. We now provide a template or worksheet for you to use. Again…if you are already working with a logic model you may utilize it, but first please share it with the Foundation for our review.

When working with a logic model, you start at the end and progress “backwards”. In other words, you should resist the temptation to start by explaining what you do, and begin instead on what you are trying to achieve. First thing is to articulate your Impact Statement. On page one of the template you are outlining your understanding of the situation and conditions which point to the importance of the project, and also potential barriers to progress:

- Articulate your Impact Statement – ideal vision for the best possible end state

- Set forth Priorities – an explanation of the situational and organizational rationale for this particular project

- List your Assumptions – those things you take for granted in planning your project

- Identify External Factors – those things that may affect your performance that are out of your control

The Schenectady Foundation Outcomes Guidebook

On page two, you get down to the details of the logic model utilizing the terms we previously defined. Start by re-writing your Impact Statement (keep the vision ever-present). Then work from right to left starting with your Project End Outcomes.

Keep working through your outcomes….then go to Outputs, Clients and finally the Inputs.

- Impact Statement – ideal vision for the best possible end state

- Project End (or Long-Term) Outcomes Statements (Behavior or Condition)

- Intermediate Outcomes Statements – usually about Action

- Short-term Outcomes Statements – usually about learning, knowledge, awareness or skill acquisition

- Outputs – what you do; how you serve your clients; the “products” of your work

- Clients – the people or community you serve and the characteristics that place them in your target population

- Inputs – those resources that you require to be successful

“What matters is not how many worms the bird feeds its young, but how well the fledgling flies.”

Project Name:

Logic Model Worksheet – Page 1

Assumptions: What are your basic assumptions underlying the planning of this project?

Impact Statement: A vision for the ultimate benefit that could be realized for the project

Priorities: This explains your rationale for doing this project – why is this important to do?

External Factors: What factors may affect the performance of the project that are “out of your control”….i.e. environmental, political, economic, funding considerations.

The Schenectady Foundation Outcomes Guidebook

8

| Short Term Outcome Target Statements | Intermediate Outcome Target Statements | Project End Outcomes Target Statements |
| --- | --- | --- |
| Often About Learning | Often About Actions | Changes in Behavior, Status or Condition |

PROJECT NAME: IMPACT STATEMENT:

Logic Model Worksheet – Page 2

| Inputs | Clients | Outputs |
| --- | --- | --- |
| The resources we need to be successful | Description and characteristics of who we serve | What we do or produce |

k oo eb

Guid s

Outcome

on i t

a

nd

Fou y

ctad ne he

Sc e

Th